## Slide 1: Rooftop Solar Program: Q3 2026 Review
Brightfield Energy (fictional) · Program office

## Slide 2: Agenda
Installations by region
Generation results
  Rooftop vs carport output
  Weather impact in August
Risks and mitigations
Q4 priorities

## Slide 3: Installations by region
Region | Quarter | Sites | Capacity (MW)
Spain | Q2 | 14 | 6.1
 | Q3 | 19 | 8.4
Portugal | Q2 | 6 | 2.2
 | Q3 | 9 | 3.5
India | Q3 | 11 | 5.0

## Slide 4: Monthly generation
Chart: Monthly generation, Q3 2026
| July | August | September
Rooftop (MWh) | 612 | 548 | 590
Carport (MWh) | 201 | 176 | 214

## Slide 5: Risks and mitigations
Inverter supply delays
  Mitigation: dual-source from two vendors
  Owner: procurement, due 15 Nov
Grid connection backlog in Portugal
  Mitigation: pre-file connection requests 90 days earlier
Panel soiling in dry months
  Mitigation: quarterly cleaning at India sites
Full risk register
Notes: Stress that the inverter delay is the only risk that threatens the Q4 target. Portugal's backlog is regulatory, not technical.

## Slide 6: Where we operate

## Slide 7: Q4 priorities
Commission 12 more sites in Spain
Close the Portugal connection backlog
Pilot battery storage at two carport sites
  Target: 15% evening self-consumption